# Willow Glen Compute Campus — Path to Site Control

Prepared for: Scott Tomsu  ·  Confidential working plan  ·  June 2026

## Objective

Move from no position to a locked, capital-efficient site-control instrument on the Willow Glen Terminal (WGT) campus footprint — without an outright purchase — while protecting the originator position and holding the one input the landowner cannot replicate.

## Guiding principles

- Control, not ownership. The instrument is a long-term ground lease (WGT retains title) and/or a purchase option — not a $175M cash acquisition. This preserves capital for interconnection, generation, and build.

- Assume a sophisticated, informed counterparty. WGT is held by Zydeco / Willow Glen Ventures; Yorktown is an energy PE firm. The River Bend comp 25 miles north has already made the monetization model public. Do not premise protection on the owner failing to understand the value — they will understand it the moment it is articulated.

- An NDA is not protection by itself. It restrains disclosure to third parties; it does not stop the owner from acting on the thesis themselves. Originator protection comes from (a) a non-circumvention / non-solicitation clause, (b) a signed exclusivity / right of first negotiation, and (c) control of a scarce input.

- Hold the scarce input. The one thing that is yours and not WGT's is confirmed Entergy/MISO load-serving capacity. Secure that inquiry independently and early.

- Stage the reveal. Lead with a teaser. Release the full economics and the monetization roadmap only after the NDA + non-circ is signed.

## Phase 0 — Before contact: protect + arm  (parallel, ~Weeks 0–3)

- Engage transactional real estate / energy counsel to paper: a mutual NDA with a non-circumvention clause, and a template exclusivity / right-of-first-negotiation for when talks turn serious. (Counsel finalizes structure; this plan is not legal advice.)

- File the Entergy large-load interconnection inquiry for the Willow Glen site — independent of WGT. Goal: a written, quantified servable-MW figure and the MISO study path. This is the moat and the single biggest diligence item in the deal.

- Prepare a two-tier document set:

  - Tier 1 — Teaser (1–2 pages): the opportunity in outline — power-ready brownfield, ground-lease structure, WGT keeps title, capital-backed — with no full economics and no monetization playbook. This is what opens the door.

  - Tier 2 — Full proposal (the revised deck): released only post-NDA. Fix the two credibility items first: reframe "450 MW already wired / nothing to confirm" as "interconnect head start, MW subject to Entergy/MISO study," and rebuild the timeline to something a reader who knows River Bend will believe.

- Confirm the capital partner (ORNN). Have the financing relationship far enough along that you can represent credible, committed capital at reveal — so you present as a sponsor with a team, not a sole originator handing over an idea.

## Phase 1 — First contact + NDA  (~Weeks 3–5)

- Direct outreach to WGT principals (GM and the Yorktown / Zydeco capital side).

- Lead with the Tier 1 teaser: a structured, capital-backed proposal to monetize the asset stack via a long-term ground lease with revenue participation, WGT retains title — specifics to follow under NDA.

- Execute the mutual NDA + non-circ before releasing Tier 2.

- Outcome: NDA signed; principal-level meeting scheduled.

## Phase 2 — Structured proposal + exclusivity  (~Weeks 5–9)

- Present the full (corrected) proposal under NDA, paired with the credibility you've assembled — the ORNN capital relationship and the Entergy interconnection data.

- Ask for 60–90 days of exclusivity / right of first negotiation, during which WGT pauses marketing the campus footprint, in exchange for committed diligence resources and (recommended) a modest non-refundable exclusivity deposit to bind seriousness.

- This is the true site-control inflection: exclusivity is what stops them shopping it.

- Outcome: signed exclusivity / ROFN.

## Phase 3 — LOI on commercial terms  (~Weeks 9–13)

- Non-binding term sheet covering: lease term, base ground rent, escalator, revenue-participation structure, retained-terminal-business carve-out, and milestones / conditions precedent — interconnection confirmation, capital close, anchor-tenant LOI.

- Make interconnection a condition precedent so you are not committed before the gate clears.

- Outcome: executed LOI.

## Phase 4 — Diligence + definitive  (~Weeks 13–24)

Run in parallel:

- Title + ALTA survey

- Substation walkdown + Entergy/MISO load-study confirmation (the gate)

- River-cooling permit confirmation

- Phase I/II environmental — retired power station; screen for legacy oil / PCB / asbestos

- Structural / geometric fit study on existing pads and switchgear foundations (reuse vs. demo/recast)

- Parish PILOT / ITEP pre-engagement (file ITEP before construction)

- Execute the definitive ground lease (or exercise the option). Site control achieved.

## What makes or breaks it

- Interconnection is the gate. Confirm servable MW before definitive. Everything downstream is contingent on it.

- Protection ≠ secrecy. Your defense is signed exclusivity + non-circ + a scarce input you hold + speed — not the owner's ignorance.

- Control is necessary, not sufficient. You still need committed capital (ORNN) and an anchor tenant / offtake to finance the build. Structure the lease with milestones so you are not exposed to multibillion-dollar construction before the deal is real.

- Speed compounds. Unhomed Anthropic Tranche-3 capacity and active hyperscaler site-walking in the corridor mean the option decays each quarter. Move — but move protected.